## Sheet1
GANTT CHART
| TITLE | WEATHER PREDICTION
[5 empty] | PHASE ZERO | [27 empty] | PHASE ONE | [20 empty] | PHASE TWO | [27 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Team Composition | All | 2026-01-12 | 2026-02-06 | 26 | 2026-03-23 M: Spring Break
Project Proposal
Introduction & Background & Problem Definition | Rick | 2026-02-07 | 2026-02-25 | 19 | bar: 2026-02-02 S to 2026-02-23 R
Methods & ML algorithm | Aytn | 2026-02-07 | 2026-02-27
Unsupervised Learning Method | Brody | 2026-02-07 | 2026-02-27
Supervised Learning Method | Austin | 2026-02-07 | 2026-02-25 | 19 | bar: 2026-02-02 S to 2026-02-23 R
Results & Discussion | Inhyeong | 2026-02-07 | 2026-02-27 | 20 | bar: 2026-02-02 S to 2026-02-23 F
Video Creation & Recording | Austin | 2026-02-07 | 2026-02-27
GitHub Page | Brody | 2026-02-07 | 2026-02-23 | 17 | bar: 2026-02-02 S to 2026-02-23 M
GitHub Repo | Rick | 2026-02-07 | 2026-02-27
Gantt chart | Inhyeong | 2026-02-07 | 2026-02-26 | 20 | bar: 2026-02-02 S to 2026-02-23 F
Contribution Table | Aytn | 2026-02-07 | 2026-02-27
Midterm Report
Model 1 (M1) Design & Selection | Brody, Austin, Rick | 2026-02-28 | 2026-03-20
M1 Data Cleaning | Brody | 2026-03-01 | 2026-03-20
M1 Data Visualization | Austin | 2026-03-02 | 2026-03-20
M1 Feature Reduction | Rick | 2026-03-03 | 2026-03-20
M1 Implementation & Coding | Inhyeong | 2026-03-04 | 2026-03-20
M1 Results Evaluation | All | 2026-03-05 | 2026-03-20
Model 2 (M2) Design & Selection | Brody, Austin, Aytn | 2026-03-06 | 2026-03-20
M2 Data Cleaning | Brody | 2026-03-07 | 2026-03-20
M2 Data Visualization | Austin | 2026-03-08 | 2026-03-20
M2 Feature Reduction | Aytn | 2026-03-09 | 2026-03-20
M2 Coding & Implementation | Rick | 2026-03-10 | 2026-03-20
M2 Results Evaluation | All | 2026-03-11 | 2026-03-20
Midterm Report | Inhyeong | 2026-03-12 | 2026-03-20
Final Report
Model 3 (M3) Design & Selection | Rick, Aytn, Inhyeong | 2026-03-21 | 2026-04-28
M3 Data Cleaning | Rick, Aytn, Inhyeong | 2026-03-21 | 2026-04-28
M3 Data Visualization | Aytn | 2026-03-21 | 2026-04-28
M3 Feature Reduction | Inhyeong | 2026-03-21 | 2026-04-28
M3 Implementation & Coding | Brody | 2026-03-21 | 2026-04-28 | bar: 2026-04-06 M to 2026-04-06 U
M3 Results Evaluation | All | 2026-03-21 | 2026-04-28 | bar: 2026-04-06 F to 2026-04-06 U
M1-M3 Comparison | All | 2026-03-21 | 2026-04-28
Video Creation & Recording | Austin | 2026-03-21 | 2026-04-28
Final Report | Inhyeong | 2026-03-21 | 2026-04-28